## Roadmap
Roadmap - Summary
Country | Office | [8 empty] | Azure | Office
| Public Announcement | CAPEX Approved | Lease Signed | TAM Award | DC Ready | Colo Ready | Dock Date | Network Complete | First Foot Print (FFP) | GA | Engineering Readiness | Current Target GA | External Public GA
Argentina | Yes | May 2011** | 2011-12-20 | 12/20/2011** | NA | 2012-10-22 | 10/22/2012** | 2012-10-22 | 2012-10-22 | 10/24/2013 10/18/2013 | 4/23/2011 4/5/2011 | 4/23/2011 4/5/2011 | May 2011

## Countries
Country | Status | Revenue Projection 3Y | Revenue Projection 5Y | TAM Restricted | TAM Unrestricted
Argentina | InProgress | 10000 | 100000 | 11111 | 11111

## Argentina_Specific
Argentina | CAPEX | 2016-01-01
| Lease Signed | Test DC1 | 2016-01-01
|  | Test DC2 | 2016-01-01
|  | Test DC3 | 2016-01-01
| Colo Ready | Test DC1 | 2015-01-02
|  | Test DC2 | 2015-01-02
| Azure Status | 1/2/2015 2/2/2019
| DC Vendors | Alpha
Beta
Gama
Delta
| Telco vendor | Beta
Theta

## Argentina_MCIO
Test DC3
Workloads | TAM Awarded | Dock Date (MCIO) | RTEG Date (MCIO) | Notes | Calendar Months/Days to Deploy (in Cal. months) | Engineering Readiness
Exchange Mgmt | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
Exchange Capacity | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
EOP Network | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
EOP Server | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
SPO Network | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
SPO Server | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
Teams (OSearch) | NA | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | TBD | Q2CY2013
Teams | NA | 2015-01-02 | 2015-01-01 | 21 weeks (TAM award to Dock) | TBD | Q2CY2013
WAC | NA | 2015-01-02 | 2015-01-01 | 21 weeks (TAM award to Dock) | 45 Days | 2011-01-01
Test DC1
Workloads | TAM Awarded | Dock Date (MCIO) | RTEG Date (MCIO) | Notes | Calendar Months/Days to Deploy (in Cal. months) | Engineering Readiness
Exchange Mgmt | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
Exchange Capacity | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
EOP Network | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
EOP Server | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
SPO Network | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
SPO Server | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
Teams (OSearch) | NA | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | TBD | Q2CY2013
Teams | NA | 2015-01-02 | 2015-01-01 | 21 weeks (TAM award to Dock) | TBD | Q2CY2013
WAC | NA | 2015-01-02 | 2015-01-01 | 21 weeks (TAM award to Dock) | 45 Days | 2011-01-01
Test DC2
Workloads | TAM Awarded | Dock Date (MCIO) | RTEG Date (MCIO) | Notes | Calendar Months/Days to Deploy (in Cal. months) | Engineering Readiness
Exchange Mgmt | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
Exchange Capacity | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
EOP Network | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
EOP Server | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
SPO Network | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
SPO Server | 2016-01-01 | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | 3 | 2001-02-02
Teams (OSearch) | NA | 2015-01-02 | 2015-01-02 | 21 weeks (TAM award to Dock) | TBD | Q2CY2013
Teams | NA | 2015-01-02 | 2015-01-01 | 21 weeks (TAM award to Dock) | TBD | Q2CY2013
WAC | NA | 2015-01-02 | 2015-01-01 | 21 weeks (TAM award to Dock) | 45 Days | 2011-01-01

## Argentina_Wrkld
Workload | Phase | Planned Start | Planned Finish | Planned Duration | Revised Start | Revised Finish | Revised Duration | Status | Remarks
Exchange | PO Approval | 2001-01-01 | 2001-01-01 | N/A | 2001-01-01 | 2001-01-01 | N/A | On Track | N/A
| Mgmt RTEG Date | 2001-01-01 | 2001-01-01 | N/A | 2001-01-01 | 2001-01-01 | N/A | On Track | N/A
| Capacity RTEG Date | 2001-01-01 | 2001-01-01 | N/A | 2001-01-01 | 2001-01-01 | N/A | On Track | N/A
| Infrastructure Deployment/Validation | 2000-01-01 | 2000-01-01 | 20 Days | 2000-01-01 | 2000-01-01 | 20 Days | On Track | N/A
| Application Deployment | 2000-01-01 | 2000-01-01 | 30 Days | 2000-01-01 | 2000-01-01 | 30 Days | On Track | N/A
| Service Readiness | 2000-01-01 | 2000-01-01 | 7 Days | 2000-01-01 | 2000-01-01 | 7 Days | On Track | N/A
| Workload Integration | 2000-01-01 | 2000-01-01 | 5 Days | 2000-01-01 | 2000-01-01 | 5 Days | On Track | N/A
| Engineering Readiness | 2001-01-01 | 2001-01-01 | 6 Days | 2001-01-01 | 2001-01-01 | 6 Days | On Track | N/A
EOP | PO Approval | 2001-01-01 | 2001-01-01 | 7 Days | 2001-01-01 | 2001-01-01 | 7 Days | On Track | N/A
| N/W RTEG Date | 2001-01-01 | 2001-01-01 | 8 Days | 2001-01-01 | 2001-01-01 | 8 Days | On Track | N/A
| Server RTEG Date | 2001-01-01 | 2001-01-01 | 9 Days | 2001-01-01 | 2001-01-01 | 9 Days | On Track | N/A
| Infrastructure Deployment/Validation | 2000-01-01 | 2000-01-01 | 20 Days | 2000-01-01 | 2000-01-01 | 20 Days | On Track | N/A
| Application Deployment | 2000-01-01 | 2000-01-01 | 30 Days | 2000-01-01 | 2000-01-01 | 30 Days | On Track | N/A
| Service Readiness | 2000-01-01 | 2000-01-01 | 7 Days | 2000-01-01 | 2000-01-01 | 7 Days | On Track | N/A
| Workload Integration | 2000-01-01 | 2000-01-01 | 5 Days | 2000-01-01 | 2000-01-01 | 5 Days | On Track | N/A
| Engineering Readiness | 2001-01-01 | 2001-01-01 | 6 Days | 2001-01-01 | 2001-01-01 | 6 Days | Delayed but No Impact | N/A
SPO | PO Approval | 2001-01-01 | 2001-01-01 | 7 Days | 2001-01-01 | 2001-01-01 | 7 Days | Delayed but No Impact | N/A
| N/w RTEG Date | 2001-01-01 | 2001-01-01 | 8 Days | 2001-01-01 | 2001-01-01 | 8 Days | Delayed but No Impact | N/A
| Server RTEG Date | 2001-01-01 | 2001-01-01 | 9 Days | 2001-01-01 | 2001-01-01 | 9 Days | Delayed but No Impact | N/A
| Infrastructure Deployment/Validation | 2000-01-01 | 2000-01-01 | 20 Days | 2000-01-01 | 2000-01-01 | 20 Days | Delayed but No Impact | N/A
| Application Deployment | 2000-01-01 | 2000-01-01 | 30 Days | 2000-01-01 | 2000-01-01 | 30 Days | Delayed but No Impact | N/A
| Service Readiness | 2000-01-01 | 2000-01-01 | 31 Days | 2000-01-01 | 2000-01-01 | 31 Days | Delayed but No Impact | N/A
| Workload Integration | 2000-01-01 | 2000-01-01 | 32 Days | 2000-01-01 | 2000-01-01 | 32 Days | Delayed but No Impact | N/A
| Engineering Readiness | 2001-01-01 | 2001-01-01 | 33 Days | 2001-01-01 | 2001-01-01 | 33 Days | Delayed and have Impact | N/A
WAC | RTEG Date | 2001-01-01 | 2001-01-01 | 34 Days | 2001-01-01 | 2001-01-01 | 34 Days | Delayed and have Impact | N/A
| Infrastructure Deployment/Validation | 2000-01-01 | 2000-01-01 | 35 Days | 2000-01-01 | 2000-01-01 | 35 Days | Delayed and have Impact | N/A
| Application Deployment | 2000-01-01 | 2000-01-01 | 36 Days | 2000-01-01 | 2000-01-01 | 36 Days | Delayed and have Impact | N/A
| Service Readiness | 2000-01-01 | 2000-01-01 | 37 Days | 2000-01-01 | 2000-01-01 | 37 Days | Delayed and have Impact | N/A
| Engineering Readiness | 2001-01-01 | 2001-01-01 | 38 Days | 2001-01-01 | 2001-01-01 | 38 Days | Delayed and have Impact | N/A
Teams | RTEG Date | 2001-01-01 | 2001-01-01 | 34 Days | 2001-01-01 | 2001-01-01 | 34 Days | Delayed and have Impact | N/A
| Infrastructure Deployment/Validation | 2000-01-01 | 2000-01-01 | 35 Days | 2000-01-01 | 2000-01-01 | 35 Days | Delayed and have Impact | N/A
| Application Deployment | 2000-01-01 | 2000-01-01 | 36 Days | 2000-01-01 | 2000-01-01 | 36 Days | Delayed and have Impact | N/A
| Service Readiness | 2000-01-01 | 2000-01-01 | 37 Days | 2000-01-01 | 2000-01-01 | 37 Days | Delayed and have Impact | N/A
| Engineering Readiness | 2001-01-01 | 2001-01-01 | 38 Days | 2001-01-01 | 2001-01-01 | 38 Days | Delayed and have Impact | N/A